## Ke hoach
CreditAtlas — kế hoạch tiếp theo
Checkpoint 17/10/2026. Tỷ lệ của toàn P1–P5, không phải phần trăm D01 hoặc production readiness.
Workspace | Đạt | Tổng yêu cầu | Tỷ lệ
P1 | 6 | 10 | 60%
P2 | 9 | 10 | 90%
P3 | 8 | 10 | 80%
P4 | 3 | 10 | 30%
P5 | 0 | 10 | 0%
Tổng | 26 | 50 | 52%
D01: R1 đạt cho sample 2012; R0/R4 còn một phần; R2/R3 chưa đạt. P5 có implementation dù ledger 0/10.
Cột Trạng thái và Ghi chú có thể cập nhật. Hoàn tất task không tự thay nghiệm thu 50 yêu cầu.
ID | Ưu tiên / phạm vi | Công việc và đầu ra | Phụ thuộc | Điều kiện đóng | Trạng thái | Ghi chú tiến độ
N01 | Ngay / shared | Hợp nhất completion, D01 release, data readiness vào một trạng thái nguồn | Ledger hiện tại | Tổng 26/50 tái tạo từ ledger; UI/docs không gọi 52% là D01; historical labels được giữ | Đang làm | API/UI derives P1-P5 from the ledger; final local runtime review remains.
N02 | Ngay / shared | N02 binds 22/27 parent groups across 123 source records; five groups have explicit dispositions. Apple FY2025 now has a four-ratio source crosswalk to SEC concepts, accession, period, USD unit and filing date. P4 browser/export passes 20 checks and one source-bound workbook passes Excel desktop. Remaining: other routes, rights/ownership, Apple point-in-time and debt-service qualification. No forecast/imputation. | P4 source-bound XLSX read-back: 7 sheets, 19 formulas, 0 errors, no external links, 39/39 upstream hashes; Excel 16.0 read-only/recalc pass. P4 JSON has source/output/lineage hashes; 32 export tests and 20 browser checks pass, 0 browser errors. Apple ratios: current 0.893292922x; liabilities/assets 79.475338283%; net margin 26.915064122%; OCF/revenue 26.788190148%. Current SEC snapshot is not PIT-qualified; interest coverage unavailable. | 27 groups statused; each KPI traces source → field → filter → formula → API/Excel; rights resolved/fenced; no unsupported estimates. | Đang làm | HMDA current-code browser QA: 46 checks, receipt app.js hashes match current code, zero page/console errors; all nine release-bound workbooks pass Excel 16.0 read-only/recalc (177 formulas, zero errors/links); 146 HMDA tests pass. Release comparability and reuse rights remain open. Apple remains one descriptive accession without point-in-time/debt-service qualification; Freddie stays a private sample, not owned exposure; HAMP gaps remain missing. No forecast; capability stays 26/50.
N03 | Ngay / shared/P4 | Registry phương pháp/giả định; gắn nhãn actual/derived/imputed/model/scenario | N02, model/scenario artifacts | Từng output số đi tới method/input; phân biệt publisher-imputed với app-imputed; không sửa frozen studies | Đang làm | NMDB Excel 16 read-only: performance suppression query 98×12; New AVE_INTRATE 28×18; Outstanding PCT_MTMLTV_GT100 54×18. HMDA fixed-2023-mix raw-source audit passes 70/70 checks for mart, attrition, denominators/amounts, reference/common-support weights, missing strata and hash stability. This verifies local calculations only, not risk prediction/fairness/causality. Remaining N03 KPI and release comparability/rights work stays open; no forecast; 26/50.
N04 | Ngay / engineering | Public regression receipt, route inventory, runtime profiling | Public checkout | Pass/fail/skip theo môi trường; đo cold/warm p50/p95 riêng; giải thích suite-view timeout | Chưa bắt đầu
N05 | Tiếp theo / market | NMDB New/Outstanding canonical aggregate mart | Raw FHFA đã audited | Unique source key, count/amount weighting và units đúng; suppression/null giữ nguyên | Đang làm | FHFA release-bound mart: 3.04M annual + 535,464 quarterly rows. Excel 16 parity passes New AVE_INTRATE (28/28) and Outstanding PCT_MTMLTV_GT100 (54/54); no imputation. Broader query coverage remains open.
N06 | Tiếp theo / market | NMDB app + workbook theo geography/market/period/measure | N05 | Filter parity API/Excel; denominator/units hiện cạnh KPI; không xuất raw vượt worksheet limit | Đang làm | D02 state reference: 79,968 ×13 source rows match; 68 suppressed rows and 14,535 blank rates retained. Excel 16 opens the 24-sheet workbook; Table filter visible; bytes unchanged. Other routes/filters remain open.
N07 | Cao / P5 | Toyota recovery components và exception ledger | Panels/certificates/EX-103 đã có | 51+29 kỳ có bridge; residual mỗi kỳ giải thích hoặc unresolved có bằng chứng; không ép zero | Đang làm | 80 periods; 3 exact ties, 77 positive residuals unresolved. Certificate identities 80/80. Residual is 12.77% of ABS-EE recoveredAmount, not recovery rate/LGD.
N08 | Cao / P5 | Nissan event/DPD/recovery exceptions theo thời gian | Nissan 23 kỳ, N07 pattern | Tái tạo ngoại lệ 07/2025 và DPD 06/2025; rule không được chọn chỉ vì khớp một kỳ | Đang làm | 23 periods: balance/count 23/23; DPD 178/184; recovery ties 17/23. Six residuals USD 8,859.23. July 2025 charge-off unresolved; June shift rejected globally (86/184).
N09 | Cao / P5 | Surveillance release gộp các deal bằng contract riêng | N07/N08 | KPI source-backed, exception drilldown, source links, Excel và analyst finding; không gọi unresolved recovery là LGD | Đã nghiệm thu | N09 release accepted across 103 periods. 83 recovery residuals unresolved; keep contract comparators separate and do not claim recovery/LGD.
N10 | Đường găng / D01 | Freddie access, pilot annual sample, release/layout audit | Authenticated access | Official receipt/hash, parser/source counts, observed cutoff và resource budget đạt | Chờ truy cập
N11 | Đường găng / D01 | Multi-vintage source/labels/support/temporal protocol | N10 | M01-006/007/015/016 đủ; final-access policy trước phân tích OOT; maturity và overlap audits | Chưa bắt đầu
N12 | Sau R2 / D01 | Constant + logistic, then bounded boosting; calibration/freeze/OOT | N11 | Cùng target/cohort, train-only features, metrics/uncertainty, frozen selection; có thể kết luận không đạt performance | Chưa bắt đầu
N13 | Có điều kiện / Ginnie | Quarterly pilot và joint key/removal semantics | Session-file path do user cung cấp | File thật/hash/layout/totals; source case riêng; không tăng Freddie vintage count | Chờ truy cập
N14 | Song song / P1 | Bondora label/maturity/as-of qualification | Snapshot/dictionary đã có | 3-way true/false/NULL giữ đúng, country/time support; no post-booking predictors | Đang làm | 789,144-row Bondora snapshot audited. 10,860 NULL labels precede maturity proxy; no post-anniversary action evidence. Partial; no model fit.
N15 | Sau qualify / P1 | Booked-loan descriptive cohort và candidate temporal benchmark | N14 | Target và availability được chốt trước fit; repeat-borrower caveat; không đóng application underwriting chỉ bằng booked data | Chưa bắt đầu
N16 | Cao / P3 | Một complete facility/debt-service case | Executed terms, payment/EIR evidence | Cash schedule + term lineage, amendment dates, source reconciliation, unavailable inputs có lý do | Chưa bắt đầu
N17 | Sau N16 / P3 | Covenant definitions/adjustments/headroom + Excel memo | N16 | Test date/threshold/adjustments đúng scope; unknown legal applicability không trả breach badge | Chưa bắt đầu
N18 | Có điều kiện / P4 | Actual contract/exposure/obligor adapter | N16 hoặc loan contracts hợp lệ | Actual schedule/EIR/group IDs và reconciled balance; no cross-currency sums | Chưa bắt đầu
N19 | Sau N18 / P4 | Research EL/ECL qualification pilot | N18 + compatible PD/recovery evidence | Matching target/horizon/population, calibrated inputs hoặc assumptions rõ; staging policy và timing audit | Chưa bắt đầu
N20 | Shared / delivery | Excel package conventions và filtered export parity | N02/N03 | Dictionary/KPI/exceptions/review consistent; no truncation, formula/number precision và native-engine checks | Đang làm | Excel 16 read-only passes: plan workbook, one performance query, two New/Outstanding exports and the 24-sheet D02 state reference. NMDB source values and suppression stay intact; remaining HMDA/PUDB/HUD routes and broader filters need QA.
N21 | Shared / engineering | CI source-only, private-data test runner, incremental route modularization | N04 | Public CI không cần private data; declared skips; dependencies pinned; existing export contracts giữ nguyên | Chưa bắt đầu
N22 | Shared / review | Review ownership, exception lifecycle và audit trail | N01/N03 | Assigned/reviewed/closed có evidence; authentication chỉ khi mở multi-user scope, không đổi local review thành bank approval | Chưa bắt đầu
N23 | Đóng gói | Năm case-study deliverables cùng một app | Các slice đã nghiệm thu | Mỗi case có business question, data, methods, results, limitations, reproduction, analyst Excel | Chưa bắt đầu
N24 | Mở rộng sau | Vietnam financial-report pilot hoặc loan-data partner | Mục tiêu sử dụng/data rights rõ | Hạch toán/đơn vị/thời điểm hợp lệ; không áp nguyên PD benchmark nước ngoài; giữ separate acceptance | Chưa bắt đầu

## 50 yeu cau
50 yêu cầu và phạm vi nghiệm thu
Ngày 16/10/2026. Đạt = 1 chỉ trong scope hiện tại. Không sửa để nâng tỷ lệ nếu chưa có evidence.
ID | Workspace | Chức năng | Đạt (1/0) | Điều kiện nghiệm thu | Khoảng trống / hướng tiếp | Nguồn scope
P1.01 | P1 | Dữ liệu & target | 1 | Client/history counts reconcile; source ID không là predictor; tháng và missing sentinels có nghĩa rõ. | Thêm cohort theo thời gian và nguồn phù hợp thị trường muốn triển khai. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_DATA_TARGET_ACCEPTANCE_VI.md
P1.02 | P1 | Application underwriting | 0 | Không dùng bill/status sau booking làm approval-time feature; có OOT và intended-use review. | Thiết kế application schema và lấy nguồn có quyền truy cập trước khi fit. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P1.03 | P1 | Behavioral model & validation | 1 | Không tune trên final test; random split được ghi rõ; bin rỗng không vẽ thành zero. | Thêm cohort ngoài thời gian; kiểm tra calibration theo population triển khai. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_BEHAVIORAL_VALIDATION_ACCEPTANCE_VI.md
P1.04 | P1 | Decision policy | 1 | Không tự reassignment khi vượt capacity; cost units không tự gọi là cash loss; validation comparisons là exploratory. | Đo chi phí vận hành thật, daily inflow và reject outcomes trước policy production. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_POLICY_SUBGROUP_ACCEPTANCE_VI.md
P1.05 | P1 | Affordability | 0 | Không suy income từ credit limit; DTI phải ghi denominator, kỳ và policy threshold. | Thêm intake income/cash-flow và debt-obligation schema. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P1.06 | P1 | Limit & pricing | 0 | Không gọi price tối ưu khi thiếu cost/take-up evidence; không mượn PD khác target. | Thu thập contract economics và thiết kế policy experiments. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P1.07 | P1 | Giải thích từng hồ sơ | 1 | Contributions cộng về prediction đúng tolerance; references/source pinned; không gọi là nguyên nhân hoặc adverse-action reason. | Kiểm tra reference sensitivity và qualification trước scoring hồ sơ mới. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_EXPLANATIONS_SAVED_ACCEPTANCE_VI.md
P1.08 | P1 | Collections workflow | 0 | Behavioral score không chứng minh uplift; không tạo SLA/contact events giả. | Thêm event-level collections data và analyst case ownership. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P1.09 | P1 | Subgroup & monitoring | 1 | Bỏ demographic predictors không chứng minh fairness; small groups không được gán ranking metrics; chưa có temporal drift. | Thu thập monitoring cohorts theo thời gian và định nghĩa escalation thresholds. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_POLICY_SUBGROUP_ACCEPTANCE_VI.md
P1.10 | P1 | Model evidence & governance | 1 | Không refit/rescore khi mở màn; benchmark Taiwan không trở thành Vietnam PD; chưa có authenticated sign-off. | Thêm model-review ownership, monitoring protocol và intended-use approval ngoài benchmark. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P1_MODEL_DOSSIER_ACCEPTANCE_VI.md
P2.01 | P2 | Source & run explorer | 1 | Không gọi sample50k là toàn thị trường; không thay extraction time bằng publication time. | Thêm authorized annual vintages và reconcile từng acquisition. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_SOURCE_RUN_ACCEPTANCE_VI.md
P2.02 | P2 | Panel quality | 1 | Unknown/gap không trở thành current; không nối qua khoảng thiếu dữ liệu. | Thêm cross-vintage quality checks và source reconciliation mới. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_PANEL_QUALITY_ACCEPTANCE_VI.md
P2.03 | P2 | Portfolio & cohorts | 1 | Zero UPB giữ riêng; count và balance có denominator khác; không cộng duplicate loan-months thành unique loans. | Bổ sung nhiều origination vintages và standardize composition comparisons. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_PORTFOLIO_ACCEPTANCE_VI.md
P2.04 | P2 | Private loan lifecycle | 1 | Không lộ raw loan ID; không coi observed timeline là forecast; không backdate confirmation. | Thêm search/paging lớn hơn và review gắn loan khi contract được chốt. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_LIFECYCLE_ACCEPTANCE_VI.md
P2.05 | P2 | Transition matrix | 1 | Không nối gaps/terminal pairs sai; năm không có pairs giữ unavailable; lifetime comparator ghi rõ scope. | Thêm temporal comparison và confidence intervals khi có đủ vintages. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_TRANSITION_ACCEPTANCE_VI.md
P2.06 | P2 | Cure & redefault | 1 | Gap/unknown phá linkage; terminal CURRENT không thành cure; follow-up thiếu không thành no-event. | Đánh giá time-to-cure/redefault trên nhiều cohorts với censoring protocol. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_CURE_ACCEPTANCE_VI.md
P2.07 | P2 | Competing outcomes | 1 | Không gọi horizon connector là monthly prediction; censored/unknown không thành negative. | Thêm survival/competing-risk model khi temporal cohorts đạt gate. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_COMPETING_ACCEPTANCE_VI.md
P2.08 | P2 | Horizon risk models | 0 | Một vintage2012 chưa đủ temporal evaluation; readiness screen không là qualified score. | Tải thêm authorized vintages và chốt R2–R3 trong PLAN_MODULE_01. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P2.09 | P2 | Observed loss bridge | 1 | Không fill missing bằng zero; sample không representative LGD calibration; UPB không tự là economic loss. | Thêm recovery timing/contract data và mature loss cohorts. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_OBSERVED_LOSS_ACCEPTANCE_VI.md
P2.10 | P2 | Evidence & review | 1 | Không sửa source bằng memo; reviewed không là authenticated bank approval. | Thêm identity/roles và formal review policy khi triển khai nhóm. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P2_FINDING_REVIEW_ACCEPTANCE_VI.md
P3.01 | P3 | SME source explorer | 1 | Không cộng files thành unique borrowers nếu chưa có identity; giữ EXEMPT/unknown/cancelled. | Thêm historical snapshots và documented loan key qualification. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_SBA_DESCRIPTIVE_ACCEPTANCE_VI.md
P3.02 | P3 | Financial normalization | 1 | Không ghép quarterly/YTD thành annual theo fiscal-year label; conflicts không chọn alias đẹp hơn. | Mở rộng issuer/taxonomy mapping và kiểm tra historical availability. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_SEC_NORMALIZATION_ACCEPTANCE_VI.md
P3.03 | P3 | Financial ratio analysis | 1 | Amendments giữ riêng; không skip gaps/concept changes; không đổi cash interest thành expense; operating-income/OCF proxies chưa là EBIT ICR, DSCR hoặc covenant. | Thêm borrower debt-service/covenant inputs và peer/sector comparisons có consistent accounting scope. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_RATIO_ANALYSIS_ACCEPTANCE_VI.md
P3.04 | P3 | Bankruptcy benchmark | 1 | Không pool five horizons thành một PD; thiếu firm IDs/publication dates nên chưa entity-disjoint/OOT. | Thu thập identified dated statements cho deployed corporate-risk study. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_BANKRUPTCY_BENCHMARK_ACCEPTANCE_VI.md
P3.05 | P3 | SBA outcomes & cohorts | 1 | Terminal snapshot không là fixed-horizon PD; post-outcome fields không làm approval predictors. | Thêm longitudinal status dates/coverage trước survival or default modeling. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_SBA_DESCRIPTIVE_ACCEPTANCE_VI.md
P3.06 | P3 | Corporate credit memo | 1 | Reviewed là self-declared analyst status; không issuer PD hoặc credit approval; thiếu source mới không ghi đè capture cũ. | Thêm issuer-event sources và borrower debt/covenant inputs cho complete credit memo. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_CORPORATE_MEMO_ACCEPTANCE_VI.md
P3.07 | P3 | Covenant workbench | 0 | Thiếu terms thì không gắn actual breach badge; SEC generic ratios không thay contract definitions. | Tạo covenant-term intake và source-backed adjustment ledger. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P3.08 | P3 | Debt & cash-flow schedule | 0 | Principal buckets không là exact payment dates, carrying debt, EAD hoặc DSCR; after-year-five open ended; debt/lease families không cộng overlap. | Thu thập instrument/facility terms, actual payment dates và interest/cash-flow inputs; qualify full debt-service schedule và covenant definitions khi inputs available. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P3.09 | P3 | Sector & concentration | 1 | Booked SBA program không đại diện toàn bộ SME economy; approval amount không tự là EAD. | Thêm comparable time snapshots và concentration uncertainty/support. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_SBA_DESCRIPTIVE_ACCEPTANCE_VI.md
P3.10 | P3 | Business review/export | 1 | Không fuzzy-match SBA name với SEC để tạo labels; không trộn reporting grains; owner chưa authenticated. | Thêm reviewer workflow/issuer events và scoped business handoff khi có inputs. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P3_BUSINESS_REVIEW_EXPORT_ACCEPTANCE_VI.md
P4.01 | P4 | Typed exposure & Excel intake | 1 | File≤20MB/50000positions; formula inputs/unsafe numeric precision bị reject; missing risk không thành zero. | Thêm column mapping theo source/facility và domain-specific Excel templates. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P4_INTAKE_CONCENTRATION_ACCEPTANCE_VI.md
P4.02 | P4 | Reconcile & concentration | 1 | Không cộng cross-currency; source observations không tự là borrower concentration; reported amount khác EAD. | Thêm obligor/group identity và explicit FX policy nếu cần global totals. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P4_INTAKE_CONCENTRATION_ACCEPTANCE_VI.md
P4.03 | P4 | Research expected loss | 0 | Không mượn PD khác target; actual source import vẫn EL unavailable nếu không có risk inputs. | Thêm calibrated probability/recovery evidence và documented economic exposure. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.04 | P4 | ECL & staging | 0 | Bullet/EIR/recovery terms hiện minh họa; stage3/POCI/revolving policies không mặc định supported; chưa accounting compliance. | Thu thập actual contract/EIR/risk evidence; review staging và recovery policy. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.05 | P4 | Scenario & stress | 0 | Không gọi macro-calibrated stress khi chỉ có assumptions; excluded positions không bị gán zero loss. | Estimate response functions từ suitable time data và validation protocol. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.06 | P4 | Movement bridge | 1 | Missing record không là default/payoff; currency migration không là FX P&L; residual phải giữ rõ. | Thêm disposition reasons và better source linkage khi có evidence. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/P4_MOVEMENT_BRIDGE_ACCEPTANCE_VI.md
P4.07 | P4 | Tail risk & concentration | 0 | Correlation/recovery chưa calibrated; thiếu obligor linkage; finite tails/CI unavailable giữ đúng; chưa capital approval. | Thêm calibrated dependence, group linkage và production convergence thresholds. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.08 | P4 | Bank observatory | 0 | USD thousand giữ đúng; institution event không là borrower default; reporting date không tự là availability date. | Thêm publication lags và stress linkage theo bank contracts. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.09 | P4 | Country observatory | 0 | Không thay missing bằng latest; ratio không cộng thành tổng; current region/income labels không historical classification. | Thêm debt/default/availability sources và documented macro stress linkage. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P4.10 | P4 | Finance review package | 0 | Reviewed không là human-authenticated sign-off; Excel notes không ghi ngược app; source values không bị sửa bởi memo. | Thêm authenticated reviewer roles và formal review policy. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.01 | P5 | Deal & terms catalog | 0 | Chưa xác minh đầy đủ agreements/amendments/legal state; terms không mặc định full contractual waterfall. | Thu thập complete agreements, amendments và term extraction review. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.02 | P5 | Collateral pool | 0 | Aggregate pool reports không là asset-level persistent panel; Ginnie/ABS-EE loan-level tracks còn thiếu. | Thêm deal-specific asset IDs/schema và collateral-history adapter. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.03 | P5 | Cash-flow projection | 0 | Reported history không được gọi là projection; chưa có complete collateral contracts. | Thiết kế collateral schedule intake và calibrate suitable behavior models. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.04 | P5 | Sequential waterfall | 0 | Cash/balance conservation; reviewer prior obligations có giả định; không gọi unconditional legal compliance. | Verify full legal regimes, prior obligations và amendments trước full contractual engine. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.05 | P5 | Tranche & triggers | 0 | Stage shortfalls không cộng thành credit loss; không prorate pool loss thành tranche loss; unsupported triggers giữ gap. | Bổ sung verified trigger state/history và loss-allocation/legal regimes. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.06 | P5 | Scenario valuation | 0 | Treasury/index OAS không là deal quote; không gọi market-calibrated ABS price. | Thu thập instrument quotes và supported projected cashflows trước calibrated valuation. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.07 | P5 | Bond sensitivity | 0 | Scope coupon-date benchmark; chưa dirty/clean/accrued/spread curve của mọi actual security. | Thêm trade/settlement dates, day-count/accrual và curve benchmark pricers. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.08 | P5 | CDS credit curve | 0 | Index OAS không thay CDS quotes; risk-neutral probability không thay borrower real-world PD. | Lấy licensed term quotes và freeze pricing conventions/benchmark. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.09 | P5 | Position & scenario comparison | 0 | Index không là executable price; actual exposure representations không double-count cùng underlying risk. | Thêm typed security-position mapping và supported instrument cashflow engines. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json
P5.10 | P5 | Surveillance & numerical evidence | 0 | Không bỏ dropped amendments/unsupported triggers; chưa live surveillance event feed. | Thêm fresh servicing periods, legal change detection và review ownership. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/COMPLETION_REQUIREMENTS_50.json

## Du lieu
Dữ liệu hiện có và mục đích dùng
Quy mô theo hồ sơ acquisition/audit đã lưu. Các nguồn khác grain và có thể chồng lấn, không cộng thành unique borrowers. | Quy mô theo receipt/acquisition. Các nguồn khác grain; không cộng thành unique borrowers. Quarterly HAMP PDFs là cohort-age snapshots, không phải loan-month records.
Nguồn | Số lượng | Đơn vị đếm | Phạm vi thời gian | Phù hợp cho | Giới hạn / việc tiếp | Báo cáo nguồn
Freddie Mac SFLLD 2012 (private; release unverified) | 50000 | loans | 2012 origination; performance through 2026-03 | P2 D01 descriptive | Local archive is private and Release 47 is not publisher-authenticated; terms and original download route unresolved; no multi-vintage qualified model. | https://www.freddiemac.com/research/datasets/sf-loanlevel-dataset
UCI350 | 30000 | clients | Taiwan 2005 | P1 behavioral benchmark | Target tháng kế tiếp; random split, chưa OOT/Vietnam PD | https://github.com/susayold/credit-atlas/blob/b997c20/docs/RETAIL_FROZEN_HOLDOUT_AND_MODEL_CARD.md
LendingClub accepted — Kaggle v3 | 2260701 | rows | 2007–2018Q4 | P1 booked-loan cohort diagnostics | 151 fields; 33 missing/invalid issue dates; feature timing, label maturity and issuer rights unqualified | https://github.com/susayold/credit-atlas/blob/b997c20/docs/LENDINGCLUB_FULL_SOURCE_VI.md
LendingClub rejected — Kaggle v3 | 27648741 | rows | 2007–2018Q4 | P1 rejected-application population only | 9 fields; 0 invalid application dates; no repayment outcome or compatible approval denominator | https://github.com/susayold/credit-atlas/blob/b997c20/docs/LENDINGCLUB_FULL_SOURCE_VI.md
Go & Grow / Bondora Loan Dataset | 789144 | loans | Issue dates 2009-02–2026-06 | P1 tri-state 12M label support | 31 fields; 86,618 true / 520,246 false / 182,280 NULL; 10,860 proxy-mature NULL unresolved; retrieval/license unqualified | https://goandgrow.eu/en/public-statistics/
NSMO v7.0 | 62359 | loans | 2013–2024; Q3/2025 outcomes | P2 D02 descriptive | 587 fields; weighting/routing/censoring; chưa model target | https://github.com/susayold/credit-atlas/blob/b997c20/docs/NSMO_D02_CASE_BUILD_PLAN_VI.md
NMDB New | 3038100 | aggregate rows | Annual 1998–2025 | Origination market context | App/API + query-scoped Excel đã tích hợp; browser visual và native Excel acceptance còn mở; VALUE1/2 tách biệt. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FHFA_NMDB_ORIGINATION_OUTSTANDING_REVIEW_VI.md
NMDB Outstanding | 535464 | aggregate rows | 2013Q1–2026Q2 | UPB / active-stock context | Không loan performance; suppressed/missing giữ riêng | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FHFA_NMDB_ORIGINATION_OUTSTANDING_REVIEW_VI.md
HMDA 2018–2025 | 12 | source release/file objects | Activity 2018–2025; release freezes 2021–2026 | D08 application/decision mix; descriptive denial analysis | 9 LAR vintages + 3 QA/reference files. Row counts by LAR release are in the source register and overlap; 2018 has 1,961 quarantined rows. No repayment/default label. | https://github.com/susayold/credit-atlas/blob/b997c20/docs/D01_PROGRESS_AND_DATA_PRIORITY_2026-10-16_VI.md
SBA FOIA | 2190504 | source records | Snapshot 2026-06-30 | P3 cohorts / sector | Status snapshot không phải fixed-horizon PD; duplicates retained | https://github.com/susayold/credit-atlas/blob/b997c20/docs/SBA_BUSINESS_DATA_CONTRACT.md
UCI365 | 43405 | statements | 5 source horizons | P3 bankruptcy benchmark | One-year subset 5.910 rows; thiếu firm IDs/publication dates | https://github.com/susayold/credit-atlas/blob/b997c20/docs/BANKRUPTCY_FINAL_MODEL_CARD.md
SEC financials | 105441 | source facts | Filing-specific | P3 ratios / memo | One Apple FY2025 accession now has 3 receipt-bound issuer artifacts; local source is not byte-identical in size to SEC-hosted copies; not a complete issuer panel or debt-service schedule. | https://github.com/susayold/credit-atlas/blob/main/docs/SEC_APPLE_2025_FILING_AND_EXPOSURE_ORIGIN_REVIEW_VI.md
FDIC | 214809 | bank-quarter reports | 42 quarters 2016Q1–2026Q2 | P4 bank observatory | Không borrower loan book; publication/merger conventions còn mở | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FDIC_BANK_PANEL_WORKFLOW.md
Freddie 2012 sample UPB diagnostic (not actual portfolio) | 9,698 loan-month rows (Mar) | Sample loan-month observations | 2012 Freddie cohort; Feb–Mar 2026 snapshots | P4 sample UPB movement / concentration diagnostic | Sample UPB only; not owned portfolio, EAD, PD or ECL. PD/LGD/EAD fields blank; no owner/obligor evidence; source release and terms remain unverified. | https://github.com/susayold/credit-atlas/blob/main/docs/SEC_APPLE_2025_FILING_AND_EXPOSURE_ORIGIN_REVIEW_VI.md
Toyota 2022-B | 2508991 | asset row-months | 51 monthly periods | P5 surveillance | 77.626 asset keys; recovery mismatch chưa resolve | https://github.com/susayold/credit-atlas/blob/b997c20/docs/TOYOTA_2024B_VALIDATION_RESEARCH_VI.md
Toyota 2024-B | 1518106 | asset row-months | 29 periods 04/2024–08/2026 | P5 surveillance | 70.254 keys; recovery tie-out 1/29 exact | https://github.com/susayold/credit-atlas/blob/b997c20/docs/TOYOTA_2024B_VALIDATION_RESEARCH_VI.md
Nissan 2024-B | 1154259 | asset row-months | 23 periods 10/2024–08/2026 | P5 external issuer source audit | 63.688 keys; event/recovery/DPD exceptions, chưa model validation | https://github.com/susayold/credit-atlas/blob/b997c20/docs/NISSAN_2024B_EXTERNAL_VALIDATION_VI.md
Ginnie production |  | not acquired | Quarterly pilot planned | Separate MBS case | Đã accept terms; chưa session-file path; sample chỉ chứng minh parser | https://github.com/susayold/credit-atlas/blob/b997c20/docs/GINNIE_MAE_LOAN_PERFORMANCE_SOURCE_REVIEW_VI.md
World Omni 2025-A | 20 | monthly certificates | Pinned servicing history | P5 cash bridge / waterfall | 2.980 typed metrics; full legal regimes / Conversion Date chưa đủ | https://github.com/susayold/credit-atlas/blob/b997c20/docs/STRUCTURED_ABS_SOURCE_WORKFLOW.md
World Bank WDI | 122892 | annual source observations; 7 indicators × 17,556 rows | Requested 1960–2025; WDI lastupdated 2026-10-08 | P4 country context; 217 economies + 49 returned aggregates; not borrower PD | 64,452 source NULLs; NPL=2,357 known and capital=2,301 known; all aggregate NPL/capital rows NULL. No carry-forward. Third-party source terms need review. | https://github.com/susayold/credit-atlas/blob/main/docs/WORLD_BANK_WDI_DATA_REVIEW_VI.md
Sovereign archive | 42519 | Entity-year; 16 selected metrics / row | Editions 2023–2026; reference years 1960–2025 | P4 sovereign-government default and revision context | 680,304 positions: 515,678 missing; 72,509 zero; 1,341 markers; 9,954 schema-absent; 68 count conflicts. Third-party rights review; not borrower PD/LGD. | https://github.com/susayold/credit-atlas/blob/main/docs/SOVEREIGN_ARCHIVE_DATA_REVIEW_VI.md
Treasury HAMP | Treasury page lists 2018-01–2023-02 update; local monthly archive only has 2022-01–2023-02. 90+ after disqualification is carried forward; paid-off/withdrawn leave future denominators. Not general PD; gap remains unresolved. | Mixed-grain records: 1,889,234 modifications + 7,982,840 monthly activity records; not loans | 14 activity dates: 2022-01–2023-02; modification effective dates 2009–2017 | Selected HAMP modified-loan workout cohort; aggregate audit only | Treasury lists updates 2018-01–2023-02; local archive has no 2018–2021 activity. Not general PD or Freddie; Not Reported is not default. | https://github.com/susayold/credit-atlas/blob/main/docs/TREASURY_HAMP_DATA_REVIEW_VI.md
FHFA PUDB 2025 | 2093767 | source records | 2025 acquisition | Mortgage credit-access mix | 66 fields; không monthly performance/default/denial population | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FHFA_PUDB_CREDIT_ACCESS_REVIEW_VI.md
NMDB Performance — All geographies | 261,856 | aggregate rows | 2002Q1–2026Q2 | P2 full-geography performance context | 13 fields; 764 suppressed + 48,028 blank/dot VALUE1; aggregate rates, not loan-level outcomes | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FHFA_NMDB_AGGREGATE_PERFORMANCE_VI.md
NMDB Performance — National/census areas | 25,088 raw / 1,568 national | aggregate rows | 2002Q1–2026Q2 | P2 national/census-area performance context | 13 fields; latest 2 quarters preliminary; separate from all-geographies and state packages | https://github.com/susayold/credit-atlas/blob/b997c20/docs/NMDB_PERFORMANCE_CONTEXT_VI.md
NMDB Performance — States | 79,968 | aggregate rows | 2002Q1–2026Q2 | P2 state/DC performance context | 13 fields; state package and route are separate; preserve suppression/missingness; not loan-level PD | https://github.com/susayold/credit-atlas/blob/b997c20/docs/FHFA_NMDB_STATE_PERFORMANCE_SOURCE_REVIEW_VI.md
LendingClub accepted — Mendeley v1 | 1,055,054 | rows | 2016Q1–2020Q2 | P1 resolved/expired-loan cohort diagnostics | 90 fields; unique id; 838,429 Fully Paid / 216,625 Charged Off; separate from Kaggle snapshot; CC BY 4.0, upstream rights review open | https://data.mendeley.com/datasets/mvvd3dnfyz/1
LendingClub issuer field dictionary | 280 | definitions checked | Acquired 2026-10-12 | P1 source semantics / candidate mapping | XLSX definitions do not prove decision-time feature availability; issuer identity and redistribution rights unqualified | https://resources.lendingclub.com/LCDataDictionary.xlsx
Treasury HAMP quarterly summaries | 20 | official PDF reports | 2018-Q1–2023-Q1; no 2021-Q3; rates through 72 months after 2009–2017 modifications | Descriptive 60+/90+ delinquency by program/vintage/age | 2,485 cohort-age rows: 2,142 reported rate pairs; 343 unavailable. 90+ carry-forward after disqualification; paid-off/withdrawn exit denominator. Local cohort API/UI explorer and filtered XLSX export implemented. Not loan-month history/PD; monthly activity gap unresolved; source PDFs stay private. | https://github.com/susayold/credit-atlas/blob/main/docs/TREASURY_HAMP_DATA_REVIEW_VI.md

## Phuong phap
Phân biệt số liệu, imputation và giả định
Không có biến forecast mới trong lượt nghiên cứu này. Các ví dụ dưới đây là phương pháp đã có hoặc gate đề xuất.
Loại giá trị | Ví dụ hiện có | Cách sử dụng và bằng chứng cần
Reported | Source UPB, certificate net losses | Giữ sign, unit, date và source reference
Derived | Count shares, ratios, movement | Ghi numerator/denominator/filter/formula và reconcile
Publisher-imputed / mixed provenance | Một số NSMO X fields | Ghi technical method nguồn; PUF thiếu item-level J flags nên không gán chắc trạng thái từng cell
Model preprocessing imputed | Bankruptcy train-median | Fit train-only, giữ missing indicators và original values; không gọi median là income/ratio quan sát
Model prediction | Frozen UCI benchmark probabilities | Target/population/horizon/model version/calibration rõ
Declared scenario | P4 PD/LGD/EAD, recovery lag, EIR, weights | Ghi ai đặt, lý do hoặc “chưa có empirical calibration”, sensitivity và intended use
Forecast | Chưa có forecast mới trong lượt này | Time-ordered backtest, naive benchmark, horizon-specific errors và intervals
Mỗi phương pháp mới cần: target/horizon; nguồn/as-of; missingness; research/baseline; công thức; validation; uncertainty; use/version.